## general_report
SEF Jira
Displaying 37 issues at 17/Sep/15 2:23 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Rank | Epic Link | Epic/Theme | Sprint | Flagged
IFB299 070 | SEVZER-41 | Single Book Page | Story | Open | Must Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-09-04 16:52 | 2015-09-17 14:01 | 2015-09-04 16:52 | [5 empty] | 0 | 1 | [8 empty] | As a user I want to be able to go to a page with a single listing on it from the main book upload page. acceptance criteria: user can select a book they want and is then redirected to the individual page | [7 empty] | 0¦ywmzc3:
IFB299 070 | SEVZER-40 | Registered Message | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-09-04 16:43 | 2015-09-17 14:01 | 2015-09-04 16:43 | [5 empty] | 0 | 1 | [8 empty] | As a user I want a message telling me i have registered to ensure my account was successfully created. Acceptance Criteria: Message only appears after a successful registration | [7 empty] | 0¦ywmzbv:
IFB299 070 | SEVZER-35 | Alert Notifications | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-28 18:38 | 2015-09-17 14:01 | 2015-08-28 19:29 | [5 empty] | 0 | 1 | [8 empty] | As a user I want to recieve a notification when some desires to borrow my textbook. Acceptance Criteria: Notification Icon always visible Notification Displays indicator when there is new notification | [7 empty] | 0¦ywmyff:
IFB299 070 | SEVZER-34 | Request To Exchange | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-28 18:35 | 2015-09-17 14:01 | 2015-08-28 19:27 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | as a user I want to able to send a borrow request to which the owner can accept. Acceptance Criteria: Button on Textbook Page Confirmation (Yes/no) of users action Automatically Send Notification To seller/Lister |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmyf7:
IFB299 070 | SEVZER-33 | View My Uploads/Listings | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-28 18:20 | 2015-09-17 14:01 | 2015-08-28 18:20 | [5 empty] | 0 | 1 | [8 empty] | As a user I want to be able to view a list of my uploaded textbooks Acceptance Criteria: user can see: Book Reference Number Title Author Condition Category(Buy/Swap/Sale) Availabilty | [7 empty] | 0¦ywmyez:
IFB299 070 | SEVZER-32 | Waiting List | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-28 17:58 | 2015-09-17 14:01 | 2015-08-28 18:50 | [5 empty] | 0 | 1 | [8 empty] | As a user I want to upload textbooks request that I am waiting for. Acceptance Criteria: Book Title Author Edition Condition Swap/Buy/Burrow | [7 empty] | 0¦ywmyer:
IFB299 070 | SEVZER-31 | Filter by: Textbooks for Swap | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-28 17:34 | 2015-09-17 14:01 | 2015-08-28 18:50 | [5 empty] | 0 | 1 |  | 3600 | 3600 |  | 0% |  |  |  | As a user I want to see a list of textbooks that are available for swap Acceptance Criteria: User can see a list textbooks available for swap |  | 0% | 0% |  | 3600 | 3600 |  | 0¦ywmyej:
IFB299 070 | SEVZER-29 | Textbook details amendments | Story | Open | Must Have | Unresolved | Unassigned | Yun-Jung An | Yun-Jung An | 2015-08-28 17:19 | 2015-09-17 14:01 | 2015-08-28 18:48 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a user, I want to be able to edit my textbook details once they are already uploaded in the event that I made a mistake Acceptance criteria: User can update previously entered details or photos of their listings. Edit button next uploads/listings |  | 0% | 0% |  | 60 | 60 | USER, developer | 0¦ywmye3: | Additional Features |  | Iteration 1
IFB299 070 | SEVZER-26 | Filter by: Books for sale | Story | In Progress | Must Have | Unresolved | Yun-Jung An | Toby Dray | Toby Dray | 2015-08-28 16:17 | 2015-09-17 14:01 | 2015-08-28 18:53 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a user I want to be able to see a list of all the textbooks that are for sale. Acceptance Criteria: User can view a page of textbooks for sale. |  | 0% | 0% |  | 60 | 60 |  | 0¦ywmydf:
IFB299 070 | SEVZER-25 | Filter by: Textbooks for borrow | Story | In Progress | Must Have | Unresolved | Yun-Jung An | Toby Dray | Toby Dray | 2015-08-28 16:16 | 2015-09-17 14:01 | 2015-08-28 18:53 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a user I want to be able to see a list of textbooks that are available for borrowing. Acceptance Criteria: User can view a page of textbooks that are available to borrow. |  | 0% | 0% |  | 60 | 60 |  | 0¦ywmyd7:
IFB299 070 | SEVZER-23 | Main Page | Story | In Progress | Must Have | Unresolved | Yun-Jung An | Toby Dray | Toby Dray | 2015-08-14 14:35 | 2015-09-17 14:01 | 2015-08-28 18:53 | [5 empty] | 0 | 1 |  | 57600 | 180 |  | 0% |  |  |  | As a user, I want a clean and navigable main page. Acceptance Criteria: Be able to navigate to page from other pages and first page users come across. |  | 0% | 0% |  | 180 | 57600 | developer | 0¦ywmpqf: | User Interface |  | Iteration 1
IFB299 070 | SEVZER-22 | Book availability | Story | Open | Must Have | Unresolved | Toby Dray | Nathan Norris | Nathan Norris | 2015-08-07 15:31 | 2015-09-17 14:01 | 2015-08-28 19:37 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user, I want to know the up-to-date availability on listed books Acceptance Criteria: Listed books display an availibilty icon. |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmmpb:
IFB299 070 | SEVZER-17 | communication | Story | Open | Must Have | Unresolved | Weijie He | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-08-05 16:59 | 2015-09-17 14:01 | 2015-08-28 19:37 | [5 empty] | 0 | 1 |  | 144000 | 288000 |  | 0% |  |  |  | As a user i want to be able to communicate with other users requirement: comment button Acceptance Criteria: User is able to post comments under textbook listing |  | 0% | 0% |  | 288000 | 144000 |  | 0¦ywmlnj:
IFB299 070 | SEVZER-16 | Remove Textbooks | Story | Open | Must Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-05 16:55 | 2015-09-17 14:01 | 2015-08-28 19:33 | [5 empty] | 0 | 1 |  | 115200 | 86400 |  | 0% |  |  |  | As a user I want to be able to remove textbook listings so users only see my available textbooks. Acceptance Criteria: User can remove textbooks through profile page |  | 0% | 0% |  | 86400 | 115200 |  | 0¦ywmkqx:
IFB299 070 | SEVZER-14 | Profile Access | Story | Open | Must Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-05 16:48 | 2015-09-17 14:02 | 2015-08-14 14:50 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user I want to be able to access my account via the main page Acceptance Criteria: User can access profile from main page |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkr2:t
IFB299 070 | SEVZER-13 | Logout | Story | Open | Must Have | Unresolved | Weijie He | Douglass Beard | Douglass Beard | 2015-08-05 16:48 | 2015-09-17 14:02 | 2015-08-28 19:41 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | As a user I want to be able to logout to ensure no one can access my account during my absence Acceptance Criteria: User is able to log out from any page or device. User is unable to reenter without username and password |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmkq1:
IFB299 070 | SEVZER-12 | Secure Storage | Story | Open | Must Have | Unresolved | Unassigned | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-08-05 16:46 | 2015-09-17 14:02 | 2015-08-14 15:25 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user i want my details to be secure so that the confidentiality of my information isn't compromised Acceptance Criteria: Password stored in hash. Database is locked. Web sever has SSH implemented. |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkr2:
IFB299 070 | SEVZER-7 | Search by Title | Story | Open | Must Have | Unresolved | Weijie He | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:31 | 2015-09-17 14:02 | 2015-08-28 17:25 | [5 empty] | 0 | 1 |  | 115200 | 115200 |  | 0% |  |  |  | as a user I want to be able to search for textbooks by Title, Author or ISBN Acceptance Criteria: Search bar is able to search all available textbooks. |  | 0% | 0% |  | 115200 | 115200 |  | 0¦ywmkr1:
IFB299 070 | SEVZER-6 | Personal Profile | Story | Open | Must Have | Unresolved | Unassigned | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:29 | 2015-09-17 14:02 | 2015-08-14 15:32 | [5 empty] | 0 | 1 |  | 144000 | 115200 |  | 0% |  |  |  | as a user I want to be able to update my details so that my information is up to date. Requirements: -logged in - Name/alias - Email - Phone number - University Acceptance Criteria: User is able to update information on personal profile page. Can modify mentioned criteria (above). User can see book listings. |  | 0% | 0% |  | 115200 | 144000 |  | 0¦ywmkqz:
IFB299 070 | SEVZER-5 | Password reset | Story | Open | Must Have | Unresolved | Unassigned | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:21 | 2015-09-17 14:02 | 2015-08-28 17:29 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | As a user I want to be able to reset my password via email incase i forget my password Acceptance Criteria: User can easily reset password using email |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmkqb:
IFB299 070 | SEVZER-4 | Textbook upload/listing | Story | In Progress | Must Have | Unresolved | Yun-Jung An | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:16 | 2015-09-17 14:02 | 2015-08-28 18:51 | [5 empty] | 0 | 1 |  | 144000 | 288000 |  | 0% |  |  |  | as a user I want to be able to upload textbook with the following details. Requirements - Book title * - ISBN * - Subject - edition * - Condition * - Description * - Swap/Sale/Borrow(drop down menu)* Acceptance Criteria: User is able to list textbooks with above listed criteria on a single page |  | 0% | 0% |  | 288000 | 144000 | Database, developer | 0¦ywmkqv: |  |  | Iteration 1
IFB299 070 | SEVZER-2 | sign up | Story | In Progress | Must Have | Unresolved | Weijie He | Toby Dray | Toby Dray | 2015-07-31 16:10 | 2015-09-17 14:02 | 2015-09-07 12:40 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | as a user, I want to be able to create a personal account for sharing textbooks. Requirements - Username * - Password * - Email * - Phone number * - Name * - University (* priority) Acceptance Criteria: User can log in and create their own personal account with above details |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkq3:
IFB299 070 | SEVZER-1 | log in | Story | In Progress | Must Have | Unresolved | Yun-Jung An | Douglass Beard | Douglass Beard | 2015-07-31 14:52 | 2015-09-17 14:02 | 2015-08-28 18:51 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | as a user I want to be able to log in so that I can access my account Requirements: Email password Acceptance criteria: User can log in using a username and password. Username is remembered. |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmkq7:
IFB299 070 | SEVZER-39 | Default Textbook Photo | Story | Open | Should Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-09-04 16:21 | 2015-09-17 14:02 | 2015-09-04 16:26 | [5 empty] | 0 | 1 |  | 3600 | 3600 |  | 0% |  |  |  | As a user I want a default textbook photo in case I don't have an image to use Acceptance Criteria: Every textbook without an imagine displays a default image. |  | 0% | 0% |  | 3600 | 3600 |  | 0¦ywmzbn:
IFB299 070 | SEVZER-38 | Default Profile Photo | Story | Open | Should Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-09-04 16:20 | 2015-09-17 14:02 | 2015-09-04 16:26 | [5 empty] | 0 | 1 |  | 3600 | 3600 |  | 0% |  |  |  | As a user I want a default imagine on my profile in case i don't have a photo Acceptance criteria: Every user without a photo has a default photo. |  | 0% | 0% |  | 3600 | 3600 |  | 0¦ywmzbf:
IFB299 070 | SEVZER-37 | Send Conformation Notification | Story | Open | Should Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-28 18:48 | 2015-09-17 14:02 | 2015-08-28 19:28 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a seller I want to be able to either accept or deny the textbook request that has been sent to me. (Look at user profile rating to decide whether to loan or not) Acceptance criteria: Notification response to buyer |  | 0% | 0% |  | 60 | 60 |  | 0¦ywmyfv:
IFB299 070 | SEVZER-30 | Filter By: Condition | Story | Open | Should Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-28 17:24 | 2015-09-17 14:02 | 2015-08-28 19:38 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a user I want to be able to sort and view books by condition status (e.g. Okay, Good, Very Good, New) |  | 0% | 0% |  | 60 | 60 |  | 0¦ywmyeb:
IFB299 070 | SEVZER-28 | Textbook Photo Upload | Story | Open | Should Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-28 17:09 | 2015-09-17 14:02 | 2015-08-28 17:09 | [5 empty] | 0 | 1 |  | 60 | 60 |  | 0% |  |  |  | As a user, I want to be able to upload a photo of the textbook I wish to list so others can view its condition |  | 0% | 0% |  | 60 | 60 |  | 0¦ywmydv:
IFB299 070 | SEVZER-18 | Newsfeed | Story | Open | Should Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-05 17:08 | 2015-09-17 14:02 | 2015-08-28 18:03 | [5 empty] | 0 | 1 |  | 288000 | 288000 |  | 0% |  |  |  | As a user I want to see listings of all textbooks available |  | 0% | 0% |  | 288000 | 288000 |  | 0¦ywmlnf:
IFB299 070 | SEVZER-15 | Search for borrow | Story | Open | Should Have | Unresolved | Unassigned | Weijie He | Weijie He | 2015-08-05 16:50 | 2015-09-17 14:02 | 2015-08-28 17:19 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | as a user, i want be able to filter books that are available for borrowing. |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmlnb:
IFB299 070 | SEVZER-10 | Tags | Story | Open | Should Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-05 16:19 | 2015-09-17 14:02 | 2015-08-07 16:21 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | As a user i want to be able to tag my textbook listing to assist users in finding my textbook. |  | 0% | 0% |  | 57600 | 57600 |  | 0¦ywmkr2:v
IFB299 070 | SEVZER-3 | Email Confirmation | Story | Open | Should Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-07-31 16:13 | 2015-09-17 14:02 | 2015-09-04 16:55 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user I want to receive a conformation email to verify my account Requirements: Username Password Be sent Asap |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkr2:r
IFB299 070 | SEVZER-21 | recommendation | Story | Open | Could Have | Unresolved | Weijie He | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-08-05 17:17 | 2015-09-17 14:02 | 2015-08-28 19:37 | [5 empty] | 0 | 1 |  | 288000 | 288000 |  | 0% |  |  |  | As a user i want to be able to recommend books for other users all-though other users recommend books for me requirement: recommendation button next to listing so you can offer textbook to friends |  | 0% | 0% |  | 288000 | 288000 |  | 0¦ywmlnr:
IFB299 070 | SEVZER-20 | Profile view listing | Story | Open | Could Have | Unresolved | Unassigned | Douglass Beard | Douglass Beard | 2015-08-05 17:16 | 2015-09-17 14:02 | 2015-08-28 19:37 | [5 empty] | 0 | 1 |  | 144000 | 144000 |  | 0% |  |  |  | As a user i want to be able to view other users profiles to browse their listing so I can get books from trusted vendors |  | 0% | 0% |  | 144000 | 144000 |  | 0¦ywmlng:
IFB299 070 | SEVZER-19 | Promotion | Story | Open | Could Have | Unresolved | Unassigned | Toby Dray | Toby Dray | 2015-08-05 17:12 | 2015-09-17 14:02 | 2015-08-07 16:26 | [5 empty] | 0 | 1 |  | 288000 | 288000 |  | 0% |  |  |  | As a user, I want to be able to promote my textbook so that they stand out. |  | 0% | 0% |  | 288000 | 288000 |  | 0¦ywmlnh:
IFB299 070 | SEVZER-9 | Review book | Story | Open | Could Have | Unresolved | Unassigned | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:33 | 2015-09-17 14:02 | 2015-08-14 17:32 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user I want to review books listed on bookhunters to inform other users of its usefulness Review book button |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkr2:i
IFB299 070 | SEVZER-8 | Review users | Story | Open | Could Have | Unresolved | Unassigned | Ahmed Omar M Alghamdi | Ahmed Omar M Alghamdi | 2015-07-31 16:33 | 2015-09-17 14:02 | 2015-08-28 17:46 | [5 empty] | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | As a user I want to be able to review other users to ensure others can see my experience Review User button on user profile page (star rating). |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmkq0:
Generated at Thu Sep 17 14:23:11 EST 2015 by Toby Dray using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.